## Goods
Country: Nigeria
Program: ACE SPED
Date: November 20, 2020
Applicable Period:January - December 2021
Project ID:
Implementing Agency: University of Nigeria, Nsukka | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN
|  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[5 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
Visual Learning Equipments, incl. video conferencing and webinars. | UNN/ACESPED/GDS/02/2021 | 1 | 100000 | National Shopping | Post | Post Review | Plan | 13/04/2021 | N/A | N/A | 03/05/2021 | 14/06/2021 | 28/06/2021 | N/A | Plan | 100000 | N/A | N/A | 26/07/2021 | N/A | 16/08/2021 | 16/08/2021
[8 empty] | 13/04 |  |  | 03/05 | 14/06 | 28/06 | [5 empty] | 26/07 |  | 16/08 | 16/08
Power and Energy Design Equipment | UNN/ACESPED/GDS/03/2021 | 2 | 75000 | National Shopping | Post | Post Review | Plan | 13/04/2021 | N/A | N/A | 03/05/2021 | 14/06/2021 | 28/06/2021 | N/A | Plan | 75000 | N/A | N/A | 26/07/2021 | N/A | 16/08/2021 | 16/08/2021
Actual
Dedicated server ,computer and networking accessories for ACE-SPED financial separate reporting at UNN Bursary | UNN/ACESPED/GDS/04/2021 | 3 | 12475 | National Shopping | Post | Post Review | Plan | 13/04/2021 | N/A | N/A | 03/05/2021 | 14/06/2021 | 28/06/2021 | N/A | Plan | 12475 | N/A | N/A | 26/07/2021 | N/A | 16/08/2021 | 16/08/2021
Actual
R & D equipment/materials for fabrication | UNN/ACESPED/GDS//05/2021 | 4 | 50000 | National Shopping | Post | Post Review | Plan | 13/04/2021 | N/A | N/A | 03/05/2021 | 14/06/2021 | 28/06/2021 | N/A | Plan | 50000 | N/A | N/A | 26/07/2021 | N/A | 16/08/2021 | 16/08/2021
[7 empty] | Actual | [7 empty] | Actual
Procurement of Project Vehicles | UNN/ACESPED/GDS//05/2021 | 5 | 160000 | Selective Tendering | Post | Post Review | Plan | 13/04/2021 | 20/04/2021 | N/A | 03/05/2021 | 14/06/2021 | 28/06/2021 | N/A | Plan | 160000 | 12/07/2021 | N/A | 26/07/2021 | N/A | 16/08/2021 | 16/08/2021
[7 empty] | Actual |  | 20/04 | [5 empty] | Actual
Equipments for Upgrading of UNN internet network (Lionet) for ACE-SPED facilities | UNN/ACESPED/GDS//05/2021 | 6 | 150000 | NCB | Post | Post Review | Plan | 13/04/2021 | 20/04/2021 | 03/05/2021 | 03/05/2021 | 14/06/2021 | 28/06/2021 | N/A | Plan | 150000 | 12/07/2021 | 26/07/2021 | 26/07/2021 | N/A | 26/08/2021 | 26/08/2021
[7 empty] | Actual |  |  | 03/05 |  |  |  |  | Actual
Equipment for ACESPED Fabrication Workshop | UNN/ACESPED/GDS//05/2021 | 7 | 125000 | NCB | Post | Post Review | Plan | 13/04/2021 | 20/04/2021 | 03/05/2021 | 03/05/2021 | 14/06/2021 | 28/06/2021 | N/A | Plan | 125000 | 12/07/2021 | 26/07/2021 | 26/07/2021 | N/A | 26/08/2021 | 26/08/2021
[7 empty] | Actual | [7 empty] | Actual
Equipment for Renewable Energy Laboratory | UNN/ACESPED/GDS//05/2021 | 8 | 95000 | National Shopping | Post | Post Review | Plan | 13/04/2021 | N/A | N/A | 03/05/2021 | 14/06/2021 | 28/06/2021 | N/A | Plan | 95000 | N/A | N/A | 26/07/2021 | N/A | 16/08/2021 | 16/08/2021
[7 empty] | Actual | [7 empty] | Actual
Equipment forAdvanced Materials Characterization Laboratory | UNN/ACESPED/GDS//05/2021 | 9 | 170000 | NCB | Post | Post Review | Plan | 13/04/2021 | 20/04/2021 | 03/05/2021 | 03/05/2021 | 14/06/2021 | 28/06/2021 | N/A | Plan | 170000 | 12/07/2021 | 26/07/2021 | 26/07/2021 | N/A | 26/08/2021 | 26/08/2021
[7 empty] | Actual | [7 empty] | Actual
Equipment for Electric Power Systems Laboratory | UNN/ACESPED/GDS//05/2021 | 10 | 325000 | NCB | Post | Post Review | Plan | 13/04/2021 | 20/04/2021 | 03/05/2021 | 03/05/2021 | 14/06/2021 | 28/06/2021 | N/A | Plan | 325000 | 12/07/2021 | 26/07/2021 | 26/07/2021 | N/A | 26/08/2021 | 26/08/2021
[7 empty] | Actual | [7 empty] | Actual
Software purchase and development | UNN/ACESPED/GDS//05/2021 | 11 | 7000 | National Shopping | Post | Post Review | Plan | 13/04/2021 | N/A | N/A | 03/05/2021 | 14/06/2021 | 28/06/2021 | N/A | Plan | 7000 | N/A | N/A | 26/07/2021 | N/A | 16/08/2021 | 16/08/2021
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 1269475 | [12 empty] | 1269475
Fill gray cells only!

## Works
Country: Nigeria
Program: Africa Centre of Excellence for Sustainable Power and Energy Development (ACE-SPED)
Date: November 20, 2020
Applicable Period: January - December 2021
Project ID:
Implementing Agency: University of Nigeria, Nsukka | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Plan |  | 1 wk |  | 1.5-3 wks
Actual
List of Contracts
Renovation of international scholars hostels with appropriate furnishings, fittings and back-up power | UNN/ACESPED/WRK//01/2021 | 1 | BOQ | National Shopping | 50000 | Post Qualification | Post Review | Plan | 06/04/2021 | N/A | N/A | 13/05/2021 | 20/05/2021 | 03/06/2021 | N/A | Plan | 50000 | 10/06/2021 | N/A | 24/06/2021 | 01/07/2021 | 25/08/2021 | 24/02/2022 | 50000
[8 empty] | Actual | [7 empty] | Actual
Renovation and upgrading of 5 no. classrooms, including the provision of teaching aids and back-up power solutions. | UNN/ACESPED/WRK//02/2021 | 2 | BOQ | National Shopping | 120000 | Post Qualification | Post Review | Plan | 06/04/2021 | N/A | N/A | 13/05/2021 | 20/05/2021 | 03/06/2021 | N/A | Plan | 120000 | 10/06/2021 | N/A | 24/06/2021 | 01/07/2021 | 25/08/2021 | 24/02/2022 | 120000
[8 empty] | Actual | [7 empty] | Actual
Construction of ACE-SPED Service Core building complex | UNN/ACESPED/WRK//02/2021 | 3 | BOQ | NCB | 1414000 | Post Qualification | Post Review | Plan | 24/09/2021 | 01/10/2021 | 13/10/2021 | 22/10/2021 | 26/11/2021 | 10/01/2022 | 20/01/2022 | Plan | 1414000 | 27/01/2022 | 28/01/2022 | 08/02/2022 | 15/02/2022 | 15/04/2022 | 14/10/2022 | 1414000
[8 empty] | Actual | [7 empty] | Actual
Renovation of Laboratory of Industrial Electronics, Power Devices and New Ene | UNN/ACESPED/WRK//02/2021 | 4 | BOQ | National Shopping | 100000 | Post Qualification | Post Review | Plan | 06/04/2021 | N/A | N/A | 13/05/2021 | 20/05/2021 | 03/06/2021 | N/A | Plan | 100000 | 10/06/2021 | N/A | 24/06/2021 | 01/07/2021 | 25/08/2021 | 24/02/2022 | 100000
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 1684000 | [11 empty] | 1684000
Fill gray cells only!
NB: Submission of BER under NCB implies submission by the Evaluation Committee to Management for Approval, and not to the Bank

## Consultants
Country/Organisation: Nigeria
Programme: Africa Centre of Excellence for Sustainable Power and Energy Development (ACE-SPED)
Date: November 20, 2020
Applicable Period: January - December 2021
Project ID:
Credit Number:
Implementing Agency: University of Nigeria, Nsukka
Request for EOI (where required)
IDA Credit No.: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation |  |  |  | Remarks
Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
Component 1:(Instititional Development)
Building Plans and Design for ACE-SPED Service Core building complex | QCBS | Lump Sum | 6000 | Prior Review | Plan | 01/04/2021 | N/A | 10/04/2021 | 24/04/2021 | 30/04/2021 | N/A | Plan | 31/05/2021 | 30/07/2021 | 06/08/2021 | N/A | 20/08/2021 | 27/08/2021 | 03/09/2021 | Plan | 10/09/2021 | N/A | 6000 | 17/09/2021 | N/A | 20/09/2021 | Plan | 22/09/2021 | 24/09/2021 | 27/09/2021 | 6,000
plan
Development of ACE-SPED website | QCBS | Lump Sum | 5000 | Post Review | Plan | 01/04/2021 | N/A | 10/04/2021 | 24/04/2021 | 30/04/2021 | N/A | Plan | 31/05/2021 | 30/07/2021 | 06/08/2021 | N/A | 20/08/2021 | 27/08/2021 | 03/09/2021 | Plan | 10/09/2021 | N/A | 5000 | 17/09/2021 | N/A | 20/09/2021 | Plan | 22/09/2021 | 24/09/2021 | 27/09/2021 | 5,000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 11000 | [19 empty] | 11000 | [7 empty] | 11000