## Goods
Country: Nigeria
Program: ACE SPED
Date: January 07, 2023
Applicable Period: January - December 2023
Project ID:
Implementing Agency: University of Nigeria, Nsukka | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN
|  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[5 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
Visual Learning Equipments, incl. video conferencing and webinars. | UNN/ACESPED/GDS/05/2023 | 1 | 63037.58 | National Shopping | Post | Post Review | Plan | 17/02/2023 | N/A | N/A | 08/03/2023 | 21/04/2023 | 05/05/2023 | N/A | Plan | 63037.58 | N/A | N/A | 02/06/2023 | N/A | 25/07/2023 | 25/07/2023
R & D equipment/materials for fabrication | UNN/ACESPED/GDS//05/2023 | 2 | 15357.86 | National Shopping | Post | Post Review | Plan | 17/02/2023 | N/A | N/A | 08/03/2023 | 21/04/2023 | 05/05/2023 | N/A | Plan | 15357.86 | N/A | N/A | 02/06/2023 | N/A | 25/07/2023 | 25/07/2023
[7 empty] | Actual | [7 empty] | Actual
Procurement of Project Vehicles | UNN/ACESPED/GDS//05/2023 | 4 | 250000 | Selective Tendering | Post | Post Review | Plan | 17/02/2023 | 24/02/2023 | N/A | 07/03/2023 | 27/03/2023 | 07/04/2023 | N/A | Plan | 250000 | 17/04/2023 | N/A | 28/04/2023 | N/A | 26/05/2023 | 26/05/2023
[7 empty] | Actual | [7 empty] | Actual
Equipments for Upgrading of UNN internet network (Lionet) for ACE-SPED facilities | UNN/ACESPED/GDS//05/2023 | 5 | 150000 | National Shopping | Post | Post Review | Plan | 17/02/2023 | N/A | N/A | 08/03/2023 | 21/04/2023 | 05/05/2023 | N/A | Plan | 150000 | N/A | N/A | 02/06/2023 | N/A | 25/07/2023 | 25/07/2023
[7 empty] | Actual | [7 empty] | Actual
Equipment for ACESPED fabrication workshop | UNN/ACESPED/GDS//05/2023 | 6 | 250000 | NCB | Post | Post Review | Plan | 17/02/2023 | 24/02/2023 | 06/03/2023 | 06/03/2023 | 06/04/2023 | 20/04/2023 | N/A | Plan | 250000 | 01/05/2023 | 15/05/2023 | 15/05/2023 | N/A | 16/06/2023 | 16/06/2023
[7 empty] | Actual | [7 empty] | Actual
Equipment for renewable energy laboratory | UNN/ACESPED/GDS//05/2023 | 7 | 190000 | National Shopping | Post | Post Review | Plan | 17/02/2023 | N/A | N/A | 08/03/2023 | 21/04/2023 | 05/05/2023 | N/A | Plan | 190000 | N/A | N/A | 02/06/2023 | N/A | 25/07/2023 | 25/07/2023
[7 empty] | Actual | [7 empty] | Actual
Equipment for advanced materials characterization laboratory | UNN/ACESPED/GDS//05/2023 | 8 | 300000 | NCB | Post | Post Review | Plan | 17/02/2023 | 24/02/2023 | 06/03/2023 | 06/03/2023 | 06/04/2023 | 20/04/2023 | N/A | Plan | 300000 | 01/05/2023 | 15/05/2023 | 15/05/2023 | N/A | 16/06/2023 | 16/06/2023
[7 empty] | Actual | [7 empty] | Actual
Equipment for electric power systems laboratory | UNN/ACESPED/GDS//05/2023 | 9 | 600000 | NCB | Post | Post Review | Plan | 17/02/2023 | 24/02/2023 | 06/03/2023 | 06/03/2023 | 06/04/2023 | 20/04/2023 | N/A | Plan | 600000 | 01/05/2023 | 15/05/2023 | 15/05/2023 | N/A | 16/06/2023 | 16/06/2023
[7 empty] | Actual | [7 empty] | Actual
Software purchase and development | UNN/ACESPED/GDS//05/2023 | 10 | 35000 | National Shopping | Post | Post Review | Plan | 17/02/2023 | N/A | N/A | 08/03/2023 | 21/04/2023 | 05/05/2023 | N/A | Plan | 35000 | N/A | N/A | 02/06/2023 | N/A | 25/07/2023 | 25/07/2023
[7 empty] | Actual | [7 empty] | Actual
Equipment for laboratory of industrial electronics, power devices and new energy system | UNN/ACESPED/GDS//05/2023 | 11 | 179833.09 | National Shopping | Post | Post Review | Plan | 17/02/2023 | N/A | N/A | 08/03/2023 | 21/04/2023 | 05/05/2023 | N/A | Plan | 179833.09 | N/A | N/A | 02/06/2023 | N/A | 25/07/2023 | 25/07/2023
[7 empty] | Actual | [7 empty] | Actual
Materials for Solar Power Mini-Grid System | UNN/ACESPED/GDS//05/2023 | 11A | 20166.91 | National Shopping | Post | Post Review | Plan | 30/12/2022 | N/A | N/A | 04/01/2023 | 13/01/2023 | 17/01/2023 | N/A | Plan | 20166.91 | N/A | N/A | 20/01/2023 | N/A | 28/01/2023 | 28/01/2023
[7 empty] | Actual | [7 empty] | Actual
Equipment for high voltage laboratory | UNN/ACESPED/GDS//05/2023 | 12 | 150000 | National Shopping | Post | Post Review | Plan | 17/02/2023 | N/A | N/A | 08/03/2023 | 21/04/2023 | 05/05/2023 | N/A | Plan | 150000 | N/A | N/A | 02/06/2023 | N/A | 25/07/2023 | 25/07/2023
[7 empty] | Actual | [7 empty] | Actual
Equipment for furnishing of 5 nos classrooms | UNN/ACESPED/GDS//05/2023 | 13 | 68163.51 | National Shopping | Post | Post Review | Plan | 17/02/2023 | N/A | N/A | 08/03/2023 | 21/04/2023 | 05/05/2023 | N/A | Plan | 68163.51 | N/A | N/A | 02/06/2023 | N/A | 25/07/2023 | 25/07/2023
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 2271558.95 | [12 empty] | 2271558.95
Fill gray cells only!

## Works
Country: Nigeria
Program: Africa Centre of Excellence for Sustainable Power and Energy Development (ACE-SPED)
Date: January 07, 2023
Applicable Period: January - December 2023
Project ID:
Implementing Agency: University of Nigeria, Nsukka | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Plan |  | 1 wk |  | 1.5-3 wks
Actual
List of Contracts
Renovation of international scholars hostels with appropriate furnishings, fittings and back-up power | UNN/ACESPED/WRK//01/2023 | 1 | BOQ | National Shopping | 70000 | Post Qualification | Post Review | Plan | 17/03/2023 | N/A | N/A | 24/03/2023 | 07/04/2023 | 21/04/2023 | N/A | Plan | 70000 | 28/04/2023 | N/A | 12/05/2023 | 19/05/2023 | 19/07/2023 | 19/12/2023 | 70000
[8 empty] | Actual | [7 empty] | Actual
Renovation of 5 no. classrooms, including the provision of teaching aids and back-up power solutions | UNN/ACESPED/WRK//02/2023 | 2 | BOQ | National Shopping | 19923.39 | Post Qualification | Post Review | Plan | 17/03/2023 | N/A | N/A | 24/03/2023 | 07/04/2023 | 21/04/2023 | N/A | Plan | 19923.39 | 28/04/2023 | N/A | 12/05/2023 | 19/05/2023 | 19/07/2023 | 19/12/2023 | 30000
[8 empty] | Actual | [7 empty] | Actual
Construction of ACE-SPED Service Core building complex | UNN/ACESPED/WRK//02/2022 | 3 | BOQ | NCB | 1400000 | Post Qualification | Post Review | Plan | 05/12/2022 | 12/12/2022 | 19/12/2022 | 29/12/2022 | 27/01/2023 | 06/03/2023 | 24/03/2023 | Plan | 1400000 | 31/03/2023 | 04/04/2023 | 14/04/2023 | 21/04/2023 | 30/03/2024 | 30/09/2024 | 1400000
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 1489923.39 | [11 empty] | 1489923.39
Fill gray cells only!
NB: Submission of BER under NCB implies submission by the Evaluation Committee to Management for Approval, and not to the Bank

## Consultants
Country/Organisation: Nigeria
Programme: Africa Centre of Excellence for Sustainable Power and Energy Development (ACE-SPED)
Date: January 07, 2023
Applicable Period: January - December 2023
Project ID:
Credit Number:
Implementing Agency: University of Nigeria, Nsukka
Request for EOI (where required)
IDA Credit No.: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation |  |  |  | Remarks
Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
Component 1:(Instititional Development)
ACE-SPED Core building complex services | QCBS | Lump Sum | 278.17 | Prior Review | Plan | 17/02/2023 | N/A | 27/02/2023 | 10/03/2023 | 16/03/2023 | N/A | Plan | 17/04/2023 | 18/05/2023 | 31/05/2023 | N/A | 14/06/2023 | 23/06/2023 | 30/06/2023 | Plan | 05/07/2023 | N/A | 278.17 | 14/07/2023 | N/A | 21/07/2023 | Plan | 24/07/2023 | 26/07/2023 | 31/07/2023 | 278.17
plan
ACE-SPED website Services | QCBS | Lump Sum | 779.14 | Post Review | Plan | 17/02/2023 | N/A | 27/02/2023 | 10/03/2023 | 16/03/2023 | N/A | Plan | 17/04/2023 | 18/05/2023 | 31/05/2023 | N/A | 14/06/2023 | 23/06/2023 | 30/06/2023 | Plan | 05/07/2023 | N/A | 779.14 | 14/07/2023 | N/A | 21/07/2023 | Plan | 24/07/2023 | 26/07/2023 | 31/07/2023 | 779.14
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Design for fabrication of relevant R & D equipments | QCBS | Lump Sum | 5000 | Post Review | Plan | 17/02/2023 | N/A | 27/02/2023 | 10/03/2023 | 16/03/2023 | N/A | Plan | 17/04/2023 | 18/05/2023 | 31/05/2023 | N/A | 14/06/2023 | 23/06/2023 | 30/06/2023 | Plan | 05/07/2023 | N/A | 5000 | 14/07/2023 | N/A | 21/07/2023 | Plan | 24/07/2023 | 26/07/2023 | 31/07/2023 | 5000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 6057.31 | [19 empty] | 6057.31 | [7 empty] | 6057.31