## Goods
Country: Nigeria
Program: ACE SPED
Date: January 14, 2025
Applicable Period: January - December 2025
Project ID:
Implementing Agency: University of Nigeria, Nsukka | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN
|  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[5 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
Visual Learning Equipments, incl. video conferencing and webinars. | UNN/ACESPED/GDS/05/2025 | 1 | 20000 | National Shopping | Post | Post Review | Plan | 06/02/2025 | N/A | N/A | 10/02/2025 | 21/02/2025 | 21/02/2025 | N/A | Plan | 20000 | 25/02/2025 | N/A | 28/02/2025 | N/A | 28/03/2025 | 28/03/2025
R & D equipment/materials for fabrication | UNN/ACESPED/GDS//05/2025 | 2 | 15000 | National Shopping | Post | Post Review | Plan | 06/02/2025 | N/A | N/A | 10/02/2025 | 21/02/2025 | 21/02/2025 | N/A | Plan | 15000 | 25/02/2025 | N/A | 28/02/2025 | N/A | 28/03/2025 | 28/03/2025
[7 empty] | Actual | [7 empty] | Actual
Equipments for Upgrading of UNN internet network (Lionet) for ACE-SPED facilities | UNN/ACESPED/GDS//05/2025 | 5 | 20000 | National Shopping | Post | Post Review | Plan | 06/02/2025 | N/A | N/A | 10/02/2025 | 21/02/2025 | 21/02/2025 | N/A | Plan | 20000 | 25/02/2025 | N/A | 28/02/2025 | N/A | 28/03/2025 | 28/03/2025
[7 empty] | Actual | [7 empty] | Actual
Equipment for ACESPED fabrication workshop | UNN/ACESPED/GDS//05/2024 | 6 | 250000 | NCB | Post | Post Review | Plan | 25/10/2024 | 22/11/2024 | 20/12/2024 | 20/12/2024 | 20/01/2025 | 27/01/2025 | N/A | Plan | 250000 | 06/02/2025 | 10/02/2025 | 10/02/2025 | N/A | 10/05/2025 | 10/05/2025
[7 empty] | Actual | [7 empty] | Actual
Equipment for renewable energy laboratory | UNN/ACESPED/GDS//05/2024 | 7 | 190000 | NCB | Post | Post Review | Plan | 25/10/2024 | 22/11/2024 | 20/12/2024 | 20/12/2024 | 20/01/2025 | 27/01/2025 | N/A | Plan | 190000 | 06/02/2025 | 10/02/2025 | 10/02/2025 | N/A | 10/05/2025 | 10/05/2025
[7 empty] | Actual | [7 empty] | Actual
Equipment for advanced materials characterization laboratory | UNN/ACESPED/GDS//05/2024 | 8 | 340000 | NCB | Post | Post Review | Plan | 25/10/2024 | 22/11/2024 | 20/12/2024 | 20/12/2024 | 20/01/2025 | 27/01/2025 | N/A | Plan | 340000 | 06/02/2025 | 10/02/2025 | 10/02/2025 | N/A | 10/05/2025 | 10/05/2025
[7 empty] | Actual | [7 empty] | Actual
Equipment for electric power systems laboratory | UNN/ACESPED/GDS//05/2025 | 9 | 20000 | National Shopping | Post | Post Review | Plan | 06/02/2025 | N/A | N/A | 10/02/2025 | 21/02/2025 | 21/02/2025 | N/A | Plan | 20000 | 25/02/2025 | N/A | 28/02/2025 | N/A | 28/03/2025 | 28/03/2025
[7 empty] | Actual | [7 empty] | Actual
Software purchase and development | UNN/ACESPED/GDS//05/2025 | 10 | 10000 | National Shopping | Post | Post Review | Plan | 06/02/2025 | N/A | N/A | 10/02/2025 | 21/02/2025 | 21/02/2025 | N/A | Plan | 10000 | 25/02/2025 | N/A | 28/02/2025 | N/A | 28/03/2025 | 28/03/2025
[7 empty] | Actual | [7 empty] | Actual
Equipment for laboratory of industrial electronics, power devices and new energy system | UNN/ACESPED/GDS//05/2025 | 11 | 10000 | National Shopping | Post | Post Review | Plan | 06/02/2025 | N/A | N/A | 10/02/2025 | 21/02/2025 | 21/02/2025 | N/A | Plan | 10000 | 25/02/2025 | N/A | 28/02/2025 | N/A | 28/03/2025 | 28/03/2025
[7 empty] | Actual | [7 empty] | Actual
Equipment for furnishing of classrooms | UNN/ACESPED/GDS//05/2025 | 13 | 100000 | National Shopping | Post | Post Review | Plan | 06/02/2025 | N/A | N/A | 10/02/2025 | 21/02/2025 | 21/02/2025 | N/A | Plan | 100000 | 25/02/2025 | N/A | 28/02/2025 | N/A | 28/03/2025 | 28/03/2025
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 975000 | [12 empty] | 975000
Fill gray cells only!

## Consultancy
Country/Organisation: Nigeria
Programme: Africa Centre of Excellence for Sustainable Power and Energy Development (ACE-SPED)
Date: January 14, 2025
Applicable Period: January - December 2025
Project ID:
Credit Number:
Implementing Agency: University of Nigeria, Nsukka
Request for EOI (where required)
IDA Credit No.: |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation |  |  |  | Remarks
Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
Component 1:(Instititional Development)
ACE-SPED website Services | QCBS | Lump Sum | 2000 | Post Review | Plan | 20/02/2025 | N/A | 28/02/2025 | 12/03/2025 | 17/03/2025 | N/A | Plan | 21/03/2025 | 04/04/2025 | 08/04/2025 | N/A | 11/04/2025 | 15/04/2025 | 18/04/2025 | Plan | 18/04/2025 | N/A | 2000 | 22/04/2025 | N/A | 29/04/2025 | Plan | 01/05/2025 | 16/05/2025 | 23/05/2025 | 779.14
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
R & D fabrication design related services | QCBS | Lump Sum | 5000 | Post Review | Plan | 20/02/2025 | N/A | 28/02/2025 | 12/03/2025 | 17/03/2025 | N/A | Plan | 21/03/2025 | 04/04/2025 | 08/04/2025 | N/A | 11/04/2025 | 15/04/2025 | 18/04/2025 | Plan | 18/04/2025 | N/A | 5000 | 22/04/2025 | N/A | 29/04/2025 | Plan | 01/05/2025 | 16/05/2025 | 23/05/2025 | 5000
[5 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Total Cost |  |  | 7000 | [19 empty] | 7000 | [7 empty] | #REF!