## Sheet1
Name of Center: ACE-SPED
Institution: University of Nigeria, Nsukka |  |  |  | On Schedule
Country: Nigeria
Center Leader: Engr. Prof. Emenike C. Ejiogu |  |  |  | Behind Schedule
Annual Workplan (January 1-June 30, 2025)
Work Plan Activities | Description | Partner Contribution (if relevant) | 2025 Y2Q1 |  |  | 2025 Y2Q2 |  |  | 2025 Y2Q3 |  |  | 2025 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated DLI Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | [6 empty] | Comments
Action 1: DLI 1 Basic Operations
Activity 1: Maintenance of ACE-SPED website | To develop a customized web-site for easy access and dissemination of Centre activities | [13 empty] | ACE-SPED website operationalized |  | 3000 | 3000 | 0 | Inf. Officer
Activity 2: Production and signing of MoUs | To establish strong partnership with Institutions | [13 empty] | A robust and benefit-oriented MoUs with partners signed |  | 5000 | 5000 | 0 | CL
0
0
Action 2: DLI 2; Development Impact of ACE-SPED | [16 empty] | 0
Activity 1: Attendance to ACE-related meetings and events outside the University | To attend ACE related meetings outside the University. | [13 empty] | Information exchange and reports on project development objectives accomplished. |  | 60000 | 60000 | 0 | CL
0
0
Action 3: DLI 3; Quantity of Students | [16 empty] | 0
Activity 1: Selection and admission of M.Eng/MSc and PhD candidates. | Candidates who applied to the various programs of the ACE-SPED are screened for admission. | [13 empty] | Qualified students are admitted based on merit. |  | 7500 | 6000 | 1500 | CL/APC
0
0
Action 4: DLI 4: Quality of Education and Research | [16 empty] | 0
Sub-activity 1: Education | [16 empty] | 0
Activity 1: Faculty and students’ support | To support faculty and students through conference/workshop/seminar attendance, research publications, internet access, scholarly visits and development of lecture materials, patents, internships, etc. | [13 empty] | Support provided to staff and students. |  | 20000 | 19000 | 1000 | CL
Activity 2: Provision of Scholarships for Thirty existing MEng/MSc and PhD sstudents. | To provide fellowship, on competitive basis, to regional students to cover cost of studies and research | [13 empty] | Regional students enrolled in the ACE are supported. |  | 75000 | 75000 | 0 | CL/APC
0
Sub-Activity 2: Research | [16 empty] | 0
Activity 1: Subscription to relevant international journals and databases. | To subscribe to relevant international journals and academic databases | [13 empty] | Subscriptions are made to relevant international journals and academic databases |  | 6000 | 5000 | 1000 | ARC/APC
Activity 2: Fabrication of relevant state-of-the-art R & D equipment | To fabricate relevant R & D equipment | [13 empty] | Relevant Research fabricated and operationalized |  | 15000 | 10000 | 5000 | CL
Activity 3: Training of faculty and technical staff on use of state-of-the-art equipment | To improve the staff proficiency in the use of state-of-the art equipment | [13 empty] | Training of faculty & technical staff for optimal utilization of state-of-the-art equipment completed |  | 12000 | 11000 | 1000 | DCL
Activity 4: Organisation of seminars/workshops and publication in journals | To document, disseminate, prototype and in extension patent research results | [13 empty] | Research results are documented |  | 6000 | 5000 | 1000 | DCL
Activity 5: Field trips | To expose students and staff to industry sector activities, on-site and data collection | [13 empty] | Field tripS executed |  | 10000 | 9000 | 1000 | ILO/ARC
Activity 6: Field trials | To ascertain the workability and performance of developed prototypes | [13 empty] | Field trials executed |  | 10000 | 8500 | 1500 | ILO/ARC
Activity 7: Software purchase and development | To purchase and develop relevant software required for energy and power research | [13 empty] | Software is developed or procured |  | 4000 | 4000 | 0 | ARC/APC
Activity 8: Facilitate exchange and sharing of information and library resources between ACE-SPED and partners | To facilitate exchange of information and resources between ACE-SPED staff and partners | [13 empty] | Information and library resources shared |  | 1000 | 800 | 200 | ILO
Activity 9 Undertake industrial liaison visits | To promote effective engagement between ACE-SPED and partners | [13 empty] | Industrial Liaison visits undertaken |  | 6000 | 5000 | 1000 | ARC/ILO
0
Sub-Activity 3: Infrastructure | [16 empty] | 0
Activity 1: Upgrading of Laboratory of Industrial Electronics, Power Devices and New Energy Systems | To furnish and equip the Industrial Electronics/New Energy Laboratory for practice orientation in energy and power research | [13 empty] | Well-equipped and functional Industrial Electronics/New Energy Laboratory |  | 10000 | 10000 | 0 | CL
Activity 2: Provision of Equipment for ACE-SPED Fabrication Workshop | To furnish and equip the Fabrication Workshop | [13 empty] | Well-equipped Fabrication Workshop |  | 5000 | 5000 | 0 | CL
Activity 3: Provision of Equipment for Renewable Energy Laboratory | To furnish and equip the Renewable Energy Laboratory | [13 empty] | Well-equipped Renewable Energy Lab. |  | 5000 | 5000 | 0 | CL
Activity 4: Provision of Equipment forAdvanced Materials Characterization Laboratory | To furnish and equip the Advanced Materials Lab | [13 empty] | Well-equipped Energy Materials Laboratory |  | 120000 | 100000 | 20000 | CL
Activity 5: Provision of Equipment for Electric Power Systems Laboratory | To furnish and equip Electric Power Systems Lab | [13 empty] | Well-equipped Electric Power Systems Laboratory |  | 462000 | 450000 | 12000 | CL
Activity 6: Conduct ESMP implementation audit for all construction activities including funding. | To conduct ESMP implementation audit | [13 empty] | ESMP implementation audit conducted |  | 20000 | 20000 | 0 | CL
Activity 7: Provide adequate signage around work areas/institution premises including Muster Point. | To provide adequte signages around work areas/institution premises | [13 empty] | Adequate signage provided |  | 2000 | 2000 | 0 | CL
Action 5: DLI 5; Relevance of Education and Research
Activity 1: Publication of ACE-SPED Journal, Bulletin and Newsletter. | Formation of the editorial board, production studio, material acquisition, production of the journal, bulletin, newsletter and promotion of the publication, feedback | [13 empty] | ACE-SPED journal, Bulletin and Newsletter |  | 15000 | 14000 | 1000 | ARC
Action 6: DLI 6; Timeliness of Fiduciary Management
Activity 1: Development of Implementation and Annual Workplan | To produce a focused overall work plan to assist in accountability & smooth operations of project. | [13 empty] | A detailed and focused work plan developed and produced |  | 2000 | 2000 | 0 | CL
Activity 2: Annual procurement, financial and external audit reports | To prepare annual procurement, financial and external audit reports | [13 empty] | Annual procurement, financial & audit reports produced |  | 6000 | 6000 | 0 | CL
Activity 3: Organize regular planning meetings s with ACE-SPED partners and major stake holders | To organize consultative forums involving all major stake holders in preparation for project take-off. | [13 empty] | Meeting held and detailed project documents produced |  | 8000 | 6000 | 2000 | DCL/ILO
Activity 4: Scheduled ACE meetings (Int’l Advisory Board, Industrial Advisory Board, Management Committee Research and Academic Co-ordination) | Scheduled ACE meetings (Int’l Advisory Board, Industrial/Sectoral Advisory Board, Management Committee Research and Academic Co-ordination) | [13 empty] | Meetings held with documentary of proceedings. |  | 10000 | 9000 | 1000 | CL
Activity 5: Final Financial Report for Project Closure | To preper a final financial report for the project | [13 empty] | A detailed final financial report produced |  | 10000 | 10000 | 0 | FMC
Activity 6: Project Completion Report | To prepare a beffitting project completion report | [13 empty] | A comprehensive pproject completion repor produced. |  | 20000 | 20000 | 0 | M&EO
Activity 7: Development of a Transition Plan (including sustaibality plan ) | To develop a transition plan (including sustainabilty research commercialization via spin-off ventures, Fee paying students, Contract research, Consultancy for industries) | [13 empty] | A transition plan developed for the project including sustainability plan (Research commercialization via spin-off ventures, Fee paying students, Contract research, Consultancy for industries) |  | 2500 | 2500 | 0 | CL
Action 7: DLI 7; Institutional Impact
Activity 1: Successful delivery of NgREN services | To have NgREN services | [13 empty] | NgREN services secured |  | 100000 | 100000 | 0 | CL
[16 empty] | Grand Total | 1038000 | 987800 | 50200